## karthik
CALL TAXI MANAGEMENT- KGISL RIDEONE
SL.NO | NAME | TIMING | DATE | PROJECT TASK | STATUS
1 | KARTHIK | 11am-4pm | 2017-12-11 | DOMAIN STUDY | COMPLETED
2 | KARTHIK | 11am-4pm | 2017-12-12 | TITLE DISCUSSION | COMPLETED
3 | KARTHIK | 11am-4pm | 2017-12-13 | PREPARATION OF ZEROTH REVIEW | COMPLETED
4 | KARTHIK | 11am-4pm | 2017-12-14 | ZEROTH REVIEW | COMPLETED
5 | KARTHIK | 11am-4pm | 2017-12-15 | INSTALLATION OF SOFTWARES & STUDYING ABOUT MAPBOX | COMPLETED
6 | KARTHIK | 11am-4pm | 2017-12-18 | WORKING ON MAPBOX | IN PROGRESS
7 | KARTHIK | 11am-4pm | 2017-12-19 | WORKING ON MAPBOX | COMPLETED
8 | KARTHIK | 11am-4pm | 2017-12-20 | CREATING A SAMPLE MODULE USING MAPBOX | IN PROGRESS
9 | KARTHIK | 11am-4pm | 2017-12-21 | LEARNING PSQL AND BASICS OF PHP | IN PROGRESS
10 | KARTHIK | 11am-3pm | 2017-12-22 | WORKING ON CAKEPHP USING TUTORIALS | IN PROGRESS
11 | KARTHIK | 11am-4pm | 2017-12-26 | CREATING A SAMPLE LOGIN PAGE | IN PROGRESS
12 | KARTHIK | 11am-4pm | 2017-12-27 | CREATING A SAMPLE LOGIN PAGE | COMPLETED
13 | KARTHIK | 11am-4pm | 2017-12-28 | WORKING ON MAP | IN PROGRESS
14 | KARTHIK | 11am-4pm | 2018-01-02 | LEARNING CAKEPHP | IN PROGRESS
15 | KARTHIK | 11am-4pm | 2018-01-03 | LEARING CAKEPHP | IN PROGRESS
16 | KARTHIK | 11am-4pm | 2018-01-04 | CREATING A DRIVER PAGE USING CAKEPHP | IN PROGRESS
17 | KARTHIK | 11am-4pm | 2018-01-05 | CREATING A DRIVER PAGE USING CAKEPHP | IN PROGRESS
18 | KARTHIK | 1PM-4PM | 2018-01-08 | CREATING A DRIVER PAGE USING CAKEPHP | COMPLETED
19 | KARTHIK | 11am-4pm | 2018-01-09 | LEARING CAKEPHP | IN PROGRESS
20 | KARTHIK | 11am-4pm | 2018-01-10 | BACK END PROCESS FOR MODULE 1 | IN PROGRESS
21 | KARTHIK | 11am-4pm | 2018-01-11 | BACK END PROCESS FOR MODULE 2 | IN PROGRESS
22 | KARTHIK | 11 am-5pm | 2018-01-17 | PREPARATION OF FIRST REVIEW | COMPLETED
23 | KARTHIK | 11am-5pm | 2018-01-19 | WORKING ON TRACKING THE LOCATION ON MOBILE USING GPS | IN PROGRESS
24 | KARTHIK | 11am-5pm | 2018-01-22 | WORKING ON FARE CALCULATION BASED ON DISTANCE AND GPS TRACKING | IN PROGRESS
25 | KARTHIK | 11am-5pm | 2018-01-24 | WORKING ON FARE CALCULATION BASED ON MAPBOX | IN PROGRESS
26 | KARTHIK | 1pm-5pm | 2018-01-25 | WORKING ON FARE CALCULATION BASED ON MAPBOX | COMPLETED
27 | KARTHIK | 1pm-5pm | 2018-01-29 | CREATING A MAILER TO SEND THE DETAILS OF DRIVER TO CUSTOMER AND BOOKING PROCESS | IN PROGRESS
28 | KARTHIK | 1pm-5pm | 2018-01-30 | LEARNING MAPBOX API TO GET THE GPS LOCATION OF THE DRIVERS WITH THEIR PLACES | COMPLETED
29 | KARTHIK | 11am-4pm | 2018-01-31 | WORKING ON AUTO EMAIL | IN PROGRESS
30 | KARTHIK | 11am-5pm | 2018-02-05 | ABSENT
31 | KARTHIK | 11am-5pm | 2018-02-06 | LEARNING FIREBASE DATABASE | IN PROGRESS
32 | KARTHIK | 11am-5pm | 2018-02-07 | WORKING ON AUTO EMAIL | COMPLETED
33 | KARTHIK | 11am-5pm | 2018-02-08 | CREATING LOGIN & REGISTER PAGE IN ANDROID | IN PROGRESS
34 | KARTHIK | 11am-5pm | 2018-02-12 | DESIGNING WEB PAGE | IN PROGRESS
35 | KARTHIK | 11am-5pm | 2018-02-13 | DESIGNING BOOKING PAGE | COMPLETED
36 | KARTHIK | 1pm-5pm | 2018-02-14 | CREATING DATABASE FOR STORING INFORMATION | IN PROGRESS
37 | KARTHIK |  | 2018-02-15 | ABSENT
38 | KARTHIK | 11am-5pm | 2018-02-21 | WORKING ON BOOKING | IN PROGRESS
39 | KARTHIK | 11am-5pm | 2018-02-22 | WORKING ON TARIFF CALCULATION | IN PROGRESS
40 | KARTHIK | 11am-5pm | 2018-02-23 | WORKING ON TARIFF CALCULATION | COMPLETED
41 | KARTHIK | 11am-5pm | 2018-02-26 | ABSENT
42 | KARTHIK | 1PM-4PM | 2018-03-05 | ABSENT
43 | KARTHIK | 1PM-4PM | 2018-03-06 | DESIGNING FRONTEND | IN PROGRESS
44 | KARTHIK | 1PM-4PM | 2018-03-07 | DESIGNING FRONTEND | IN PROGRESS
45 | KARTHIK | 11am-4pm | 2018-03-08 | ASSIGNING DRIVER TO GET ALERT | IN PROGRESS
46 | KARTHIK | 11am-4pm | 2018-03-12 | ASSIGNING DRIVER TO GET ALERT | IN PROGRESS
47 | KARTHIK | 8:30am-4pm | 2018-03-14 | ASSIGNING DRIVER TO GET ALERT | COMPLETED

## kavyamalar
CALL TAXI MANAGEMENT- KGISL RIDEONE
SL.NO | NAME | TIMING | DATE | PROJECT TASK | STATUS
1 | KAVYAMALAR | 11am-4pm | 2017-12-11 | DOMAIN STUDY | COMPLETED
2 | KAVYAMALAR | 11am-4pm | 2017-12-12 | TITLE DISCUSSION | COMPLETED
3 | KAVYAMALAR | 11am-4pm | 2017-12-13 | PREPARATION OF ZEROTH REVIEW | COMPLETED
4 | KAVYAMALAR | 11am-4pm | 2017-12-14 | ZEROTH REVIEW | COMPLETED
5 | KAVYAMALAR | 11am-4pm | 2017-12-15 | INSTALLATION OF SOFTWARES & STUDYING ABOUT PSQL | COMPLETED
6 | KAVYAMALAR | 11am-4pm | 2017-12-18 | WENT TO A PLACEMENT DRIVE
7 | KAVYAMALAR | 11am-4pm | 2017-12-19 | WORKING ON PSQL | IN PROGRESS
8 | KAVYAMALAR | 11am-4pm | 2017-12-20 | LEARNING PSQL USING TUTORIALS AND PRACTICED SOME PROGRAMS | IN PROGRESS
9 | KAVYAMALAR | 11am-4pm | 2017-12-21 | DISCUSSED ABOUT OPENSTREETMAP AND BASIC OF PHP | COMPLETED
10 | KAVYAMALAR | 11am-3pm | 2017-12-22 | WORKING ON CAKEPHP USING TUTORIALS | IN PROGRESS
11 | KAVYAMALAR | 11am-3pm | 2017-12-26 | WORKFLOW FOR CALL TAXI MANAGEMENT | COMPLETED
12 | KAVYAMALAR | 11am-4pm | 2017-12-27 | WENT TO A PLACEMENT DRIVE
13 | KAVYAMALAR | 11am-4pm | 2017-12-28 | WORKING ON MAP | IN PROGRESS
14 | KAVYAMALAR | 11am-4pm | 2018-01-02 | LEARNING CAKEPHP BASICS | IN PROGRESS
15 | KAVYAMALAR | 11am-4pm | 2018-01-03 | LEARNING CAKEPHP BASICS | IN PROGRESS
16 | KAVYAMALAR | 11am-4pm | 2018-01-04 | WENT TO A PLACEMENT DRIVE
17 | KAVYAMALAR | 1AM-4PM | 2018-01-05 | CREATING A DRIVER PAGE USING CAKEPHP | IN PROGRESS
18 | KAVYAMALAR | 11am-4pm | 2018-01-08 | CREATING A DRIVER PAGE USING CAKEPHP | COMPLETED
19 | KAVYAMALAR |  | 2018-01-09 | ABSENT
20 | KAVYAMALAR | 11am-4pm | 2018-01-10 | BACK END PROCESS FOR MODULE 1 | IN PROGRESS
21 | KAVYAMALAR | 11am-4pm | 2018-01-11 | BACK END PROCESS FOR MODULE 2 | IN PROGRESS
22 | KAVYAMALAR | 11am-5pm | 2018-01-17 | PREPARATION OF FIRST REVIEW | COMPLETED
23 | KAVYAMALAR | 11am-5pm | 2018-01-19 | WORKING ON FARE CALCULATION BASED ON DISTANCE | IN PROGRESS
24 | KAVYAMALAR | 11am-5pm | 2018-01-22 | WORKING ON FARE CALCULATION BASED ON DISTANCE AND GPS TRACKING | IN PROGRESS
25 | KAVYAMALAR | 11am-5pm | 2018-01-24 | WORKING ON FARE CALCULATION BASED ON MAPBOX | IN PROGRESS
26 | KAVYAMALAR | 1pm-5pm | 2018-01-25 | WORKING ON FARE CALCULATION BASED ON MAPBOX | COMPLETED
27 | KAVYAMALAR | 1pm-5pm | 2018-01-29 | CREATING A MAILER TO SEND THE DETAILS OF DRIVER TO CUSTOMER AND BOOKING PROCESS | IN PROGRESS
28 | KAVYAMALAR | 1pm-5pm | 2018-01-30 | LEARNING MAPBOX API TO GET THE GPS LOCATION OF THE DRIVERS WITH THEIR PLACES | COMPLETED
29 | KAVYAMALAR |  | 2018-01-31 | ABSENT
30 | KAVYAMALAR | 11am-5pm | 2018-02-05 | INSTALLATION OF ANDROID STUDIO | COMPLETED
31 | KAVYAMALAR | 11am-5pm | 2018-02-06 | LEARNING FIREBASE DATABASE | IN PROGRESS
32 | KAVYAMALAR | 11am-5pm | 2018-02-07 | WORKING ON AUTO EMAIL | COMPLETED
33 | KAVYAMALAR | 11am-5pm | 2018-02-08 | CREATING LOGIN & REGISTER PAGE IN ANDROID | IN PROGRESS
34 | KAVYAMALAR | 11am-5pm | 2018-02-12 | DESIGNING ADROID | IN PROGRESS
35 | KAVYAMALAR | 11am-5pm | 2018-02-03 | DESIGNING NAVIGATION PAGE | COMPLETED
36 | KAVYAMALAR | 1pm-5pm | 2018-02-14 | CREATING DATABASE FOR STORING INFORMATION | IN PROGRESS
37 | KAVYAMALAR | 11am-5pm | 2018-02-15 | CREATING DATABASE FOR STORING INFORMATION | COMPLETED
38 | KAVYAMALAR | 11am-5pm | 2018-02-21 | WORKING ON TARIFF CALCULATION | IN PROGRESS
39 | KAVYAMALAR |  | 2018-02-22 | ABSENT
40 | KAVYAMALAR |  | 2018-02-23 | ABSENT
41 | KAVYAMALAR | 11am-5pm | 2018-02-26 | WORKING ON BOOKING | IN PROGRESS
42 | KAVYAMALAR | 1pm-4pm | 2018-03-05 | WORKING ON BOOKING | COMPLETED
43 | KAVYAMALAR | 1PM-4PM | 2018-03-06 | DESIGNING FRONTEND | IN PROGRESS
44 | KAVYAMALAR |  | 2018-03-07 | ABSENT
45 | KAVYAMALAR | 11am-4pm | 2018-03-08 | ASSIGNING DRIVER TO GET ALERT | IN PROGRESS
46 | KAVYAMALAR |  | 2018-03-12 | ABSENT
47 | KAVYAMALAR | 8:30am-4pm | 2018-03-14 | ASSIGNING DRIVER TO GET ALERT | COMPLETED
Note on E1: Windows User:

## gokul
CALL TAXI MANAGEMENT- KGISL RIDEONE
SL.NO | NAME | TIMING | DATE | PROJECT TASK | STATUS
1 | GOKUL | 11am-4pm | 2017-12-11 | ABSENT
2 | GOKUL | 11am-4pm | 2017-12-12 | ABSENT
3 | GOKUL | 11am-4pm | 2017-12-13 | PREPARATION OF ZEROTH REVIEW | COMPLETED
4 | GOKUL | 11am-4pm | 2017-12-14 | ZEROTH REVIEW | COMPLETED
5 | GOKUL | 11am-4pm | 2017-12-15 | LEARNING ABOUT CROSS PLATFORM | COMPLETED
6 | GOKUL | 11am-4pm | 2017-12-18 | WORKING ON IONIC PLATFORM | IN PROGRESS
7 | GOKUL | 11am-4pm | 2017-12-19 | WORKING ON IONIC PLATFORM | IN PROGRESS
8 | GOKUL | 11am-12.15pm | 2017-12-20 | WORKING ON IONIC PLATFORM | IN PROGRESS
9 | GOKUL | 1pm-4pm | 2017-12-21 | LEARNED ABOUT OPENSTREETMAP AND CSS | IN PROGRESS
10 | GOKUL | 11am-3pm | 2017-12-22 | WORKING ON CAKEPHP USING TUTORIALS | IN PROGRESS
11 | GOKUL | 11am-4pm | 2017-12-26 | WORKING ON CAKEPHP USING TUTORIALS | COMPLETED
12 | GOKUL | 11am-4pm | 2017-12-27 | ABSENT
13 | GOKUL | 11am-4pm | 2017-12-28 | WORKING ON MAP | IN PROGRESS
14 | GOKUL | 11am-4pm | 2018-01-02 | LEARNING ANDROID | IN PROGRESS
15 | GOKUL | 1pm-4pm | 2018-01-03 | LEARNING ANDROID | IN PROGRESS
16 | GOKUL | 11am-4pm | 2018-01-04 | LEARNING JAVA | IN PROGRESS
17 | GOKUL | 11am-4pm | 2018-01-05 | LEARNING JAVA | IN PROGRESS
18 | GOKUL | 11am-4pm | 2018-01-08 | ABSENT
19 | GOKUL | 11am-4pm | 2018-01-09 | LEARING ABOUT ANDROID STUDIO | IN PROGRESS
20 | GOKUL | 11am-4pm | 2018-01-10 | STUDYING THE LAYOUTS | IN PROGRESS
21 | GOKUL | 11am-4pm | 2018-01-11 | STUDYING THE LAYOUTS | COMPLETED
22 | GOKUL | 11am-5pm | 2018-01-17 | PREPARATION OF FIRST REVIEW | COMPLETED
23 | GOKUL |  | 2018-01-19 | ABSENT
24 | GOKUL | 11am-5pm | 2018-01-22 | DESIGNING THE DRIVER APPLICATION | IN PROGRESS
25 | GOKUL | 11am-5pm | 2018-01-24 | DESIGNING THE DRIVER APPLICATION | IN PROGRESS
26 | GOKUL | 1pm-5pm | 2018-01-25 | DESIGNING THE DRIVER APPLICATION | COMPLETED
27 | GOKUL |  | 2018-01-29 | ABSENT
28 | GOKUL | 1pm-5pm | 2018-01-30 | DESIGNING THE PASSENGER APPLICATION | IN PROGRESS
29 | GOKUL | 11am-4pm | 2018-01-31 | LEARNING ON UDACITY | IN PROGRESS
30 | GOKUL | 11am-5pm | 2018-02-05 | LEARNING ON UDACITY | IN PROGRESS
31 | GOKUL | 11am-5pm | 2018-02-06 | LEARNING ON UDACITY | IN PROGRESS
32 | GOKUL | 11am-5pm | 2018-02-07 | LEARNING ON UDACITY | IN PROGRESS
33 | GOKUL |  | 2018-02-08 | ABSENT
34 | GOKUL | 11am-12.15pm | 2018-02-12 | LEARNING ON UDACITY | IN PROGRESS
35 | GOKUL | 11am-5pm | 2018-02-13 | LEARNING ON UDACITY | IN PROGRESS
36 | GOKUL | 1pm-5pm | 2018-02-14 | LEARNING ON UDACITY | IN PROGRESS
37 | GOKUL | 11am-5pm | 2018-02-15 | LEARNING ON UDACITY | IN PROGRESS
38 | GOKUL | 11am-5pm | 2018-02-21 | LEARNING ON UDACITY | IN PROGRESS
39 | GOKUL | 11am-5pm | 2018-02-22 | LEARNING ON UDACITY | IN PROGRESS
40 | GOKUL | 11am-5pm | 2018-02-23 | LEARNING ON UDACITY | IN PROGRESS
41 | GOKUL | 11am-5pm | 2018-02-26 | LEARNING ON UDACITY | IN PROGRESS
42 | GOKUL | 1pm-4pm | 2018-03-05 | LEARNING ON UDACITY | IN PROGRESS
43 | GOKUL | 1pm-4pm | 2018-03-06 | LEARNING ON UDACITY | IN PROGRESS
44 | GOKUL | 1pm-4pm | 2018-03-07 | LEARNING ON UDACITY | IN PROGRESS
45 | GOKUL | 1pm-4pm | 2018-03-08 | LEARNING ON UDACITY | IN PROGRESS
46 | GOKUL | 11am-4pm | 2018-03-12 | LEARNING ON UDACITY | IN PROGRESS
47 | GOKUL | 8:30am-4pm | 2018-03-14 | LEARNING ON UDACITY | IN PROGRESS

## monisha
CALL TAXI MANAGEMENT- KGISL RIDEONE
SL.NO | NAME | TIMING | DATE | PROJECT TASK | STATUS
1 | MONISHA | 11am-4pm | 2017-12-11 | DOMAIN STUDY | COMPLETED
2 | MONISHA | 11am-4pm | 2017-12-12 | TITLE DISCUSSION | COMPLETED
3 | MONISHA | 11am-4pm | 2017-12-13 | PREPARATION OF ZEROTH REVIEW | COMPLETED
4 | MONISHA | 11am-4pm | 2017-12-14 | ZEROTH REVIEW | COMPLETED
5 | MONISHA | 11am-4pm | 2017-12-15 | INSTALLATION OF SOFTWARES & STUDYING ABOUT CAKEPHP | COMPLETED
6 | MONISHA | 11am-4pm | 2017-12-18 | STUDYING ABOUT PSQL | IN PROGRESS
7 | MONISHA | 11am-4pm | 2017-12-19 | WORKING ON PSQL | IN PROGRESS
8 | MONISHA | 11am-4pm | 2017-12-20 | LEARNING PSQL USING TUTORIALS AND PRACTICED SOME PROGRAMS | IN PROGRESS
9 | MONISHA | 11am-4pm | 2017-12-21 | DISCUSSED ABOUT OPENSTREETMAP AND BASIC OF PHP | COMPLETED
10 | MONISHA | 11am-3pm | 2017-12-22 | WORKING ON CAKEPHP USING TUTORIALS | IN PROGRESS
11 | MONISHA | 11am-4pm | 2017-12-26 | WORKFLOW FOR CALL TAXI MANAGEMENT | COMPLETED
12 | MONISHA | 11am-4pm | 2017-12-27 | WORKING ON CAKEPHP USING TUTORIALS | IN PROGRESS
13 | MONISHA | 11am-4pm | 2017-12-28 | WORKING ON MAP | IN PROGRESS
14 | MONISHA |  | 2018-01-02 | ABSENT
15 | MONISHA | 11am-4pm | 2018-01-03
16 | MONISHA | 11am-4pm | 2018-01-04 | CREATING A DRIVER PAGE USING CAKEPHP | IN PROGRESS
17 | MONISHA | 11am-4pm | 2018-01-05 | CREATING A DRIVER PAGE USING CAKEPHP | IN PROGRESS
18 | MONISHA |  | 2018-01-08 | ABSENT
19 | MONISHA |  | 2018-01-09 | ABSENT
20 | MONISHA | 1PM-4PM | 2018-01-10 | BACK END PROCESS FOR MODULE 1 | IN PROGRESS
21 | MONISHA | 11am-4pm | 2018-01-11 | BACK END PROCESS FOR MODULE 2 | IN PROGRESS
22 | MONISHA | 11am-5pm | 2018-01-17 | PREPARATION OF FIRST REVIEW | COMPLETED
23 | MONISHA | 11am-5pm | 2018-01-19 | WORKING ON FARE CALCULATION BASED ON DISTANCE | IN PROGRESS
24 | MONISHA | 11am-5pm | 2018-01-22 | WORKING ON FARE CALCULATION BASED ON DISTANCE AND GPS TRACKING | IN PROGRESS
25 | MONISHA | 11am-5pm | 2018-01-24 | WORKING ON FARE CALCULATION BASED ON MAPBOX | IN PROGRESS
26 | MONISHA | 1pm-5pm | 2018-01-25 | WORKING ON FARE CALCULATION BASED ON MAPBOX | COMPLETED
27 | MONISHA |  | 2018-01-29 | ABSENT
28 | MONISHA |  | 2018-01-30 | ABSENT
29 | MONISHA | 11am-4pm | 2018-01-31 | WORKING ON AUTO EMAIL | IN PROGRESS
30 | MONISHA | 11am-5pm | 2018-02-05 | INSTALLATION OF ANDROID STUDIO | COMPLETED
31 | MONISHA | 11am-5pm | 2018-02-06 | LEARNING FIREBASE DATABASE | IN PROGRESS
32 | MONISHA | 11am-5pm | 2018-02-07 | WORKING ON AUTO EMAIL | COMPLETED
33 | MONISHA | 11am-5pm | 2018-02-08 | CREATING LOGIN & REGISTER PAGE IN ANDROID | IN PROGRESS
34 | MONISHA | 11am-5pm | 2018-02-12 | DESIGNING ADROID | IN PROGRESS
35 | MONISHA | 11am-5pm | 2018-02-03 | DESIGNING NAVIGATION PAGE | COMPLETED
36 | MONISHA | 1pm-5pm | 2018-02-14 | CREATING DATABASE FOR STORING INFORMATION | IN PROGRESS
37 | MONISHA | 11am-5pm | 2018-02-15 | CREATING DATABASE FOR STORING INFORMATION | COMPLETED
38 | MONISHA | 11am-5pm | 2018-02-21 | WORKING ON TARIFF CALCULATION | IN PROGRESS
39 | MONISHA | 11am-5pm | 2018-02-22 | WORKING ON TARIFF CALCULATION | IN PROGRESS
40 | MONISHA | 11am-5pm | 2018-02-23 | WORKING ON TARIFF CALCULATION | COMPLETED
41 | MONISHA | 11am-5pm | 2018-02-26 | WORKING ON BOOKING | IN PROGRESS
41 | MONISHA | 11am-5pm | 2018-03-15 | WORKING ON BOOKING | COMPLETED
43 | MONISHA | 1PM-4PM | 2018-03-06 | DESIGNING FRONTEND | IN PROGRESS
44 | MONISHA | 1PM-4PM | 2018-03-07 | DESIGNING FRONTEND | IN PROGRESS
45 | MONISHA | 11am-4pm | 2018-03-08 | ASSIGNING DRIVER TO GET ALERT | IN PROGRESS
46 | MONISHA | 11am-4pm | 2018-03-12 | ASSIGNING DRIVER TO GET ALERT | IN PROGRESS
47 | MONISHA | 8:30am-4pm | 2018-03-14 | ASSIGNING DRIVER TO GET ALERT | COMPLETED